## Sheet1
Leader Led Tool Kit Development Progress
S/No | Functionalities | Owner | Target Start date | Target Completion Date | Actual Start Date | Actual Completion Date | Status | Remarks
User Interface
1 | Home | MQ | 2015-05-18 | 2015-05-18 |  |  | Completed
2 | Client Profile | MQ | 2015-05-18 | 2015-05-18 |  |  | Completed
3 | Client Detail | MQ | 2015-05-19 | 2015-05-20
4 | Client Listing | MQ | 2015-05-18 | 2015-05-18 |  |  | Completed
5 | Client Attendance | MQ | 2015-05-19 | 2015-05-20
6 | Equipment | MQ | 2015-05-18 | 2015-05-18 |  |  | Completed
7 | Equipment - rental | MQ | 2015-05-19 | 2015-05-19 |  |  | Completed
8 | Equipment Listing | MQ | 2015-05-19 | 2015-05-19 |  |  | Completed
9 | Equipment Rental Listing | MQ | 2015-05-19 | 2015-05-19 |  |  | Completed
10 | Courses | MQ | 2015-05-19 | 2015-05-19 |  |  | Completed | Course Page has link to go to Course Registration Page, Course thus Registration Page need to be changed. Pending: Course Registration Page
11 | Courses Listing | MQ | 2015-05-19 | 2015-05-19 |  |  | Completed
12 | Courses Registration Listing | MQ | 2015-05-19 | 2015-05-19 |  |  | Completed
13 | Enquiry Create | MQ | 2015-05-19 | 2015-05-20
14 | Enquiry Listing | MQ | 2015-05-19 | 2015-05-20
15 | Appointment - Service Appointment booking | ZK | 2015-05-18 | 2015-05-19 |  |  | In Progress | Add/edit / next button
16 | Invoice Listing | ZK | 2015-05-18 | 2015-05-19 |  |  |  | Add/edit / next button
17 | Setup Service Centre | ZK | 2015-05-18 | 2015-05-19 |  |  |  | Left with Color on the left panel
18 | Setup Subsidy | ZK | 2015-05-18 | 2015-05-19 |  |  |  | Add/edit / next button
19 | Setup Means Test Listing | ZK | 2015-05-20 | 2015-05-20 |  |  |  | Add/edit / next button
20 | Setup Payment Rate | ZK | 2015-05-20 | 2015-05-20 |  |  |  | Add/edit / next button
21 | Setup Programmes | ZK | 2015-05-20 | 2015-05-20 |  |  |  | Add/edit / next button
22 | Remove Constiteuncy | ZK | 2015-05-18 | 2015-05-18 |  |  | Completed | Add/edit / next button
23 | Remove Information Source | ZK | 2015-05-18 | 2015-05-18 |  |  | Completed | Add/edit / next button
24 | Remove Corporate Discount | ZK | 2015-05-18 | 2015-05-18 |  |  | Completed | Add/edit / next button
25 | Setup Service Fee | ZK | 2015-05-18 | 2015-05-19 |  |  |  | Add/edit / next button
26 | User | ZK | 2015-05-20 | 2015-05-20 |  |  |  | Add/edit / next button
27 | Report | ZK | 2015-05-20 | 2015-05-20 |  |  |  | Add/edit / next button
28 | Role | ZK | 2015-05-20 | 2015-05-20 |  |  |  | Add/edit / next button
Development Features
1 | Filter for client at Home | ZK | 2015-05-20 | 2015-05-20
2 | Values of each Client listed at Home to be real data, currently is fake | ZK | 2015-05-21 | 2015-05-21
3 | Report for Client Arrears with export to excel | MQ | 2015-05-21 | 2015-05-21
4 | Report for Attendance with export to excel | MQ | 2015-05-22 | 2015-05-22
5 | Report for existing client in each centre and programs with export to excel. --> Total Clients Accumulative | ZK | 2015-05-22 | 2015-05-22
6 | Report for withdrawal for each centre | ZK | 2015-05-25 | 2015-05-25
7 | Report for Transport services required for each centre | ZK | 2015-05-26 | 2015-05-27
Deployment to Staging
1 | Deploy to staging | ZK | 2015-05-19 | 2015-05-19