## Sheet1
Leader Led Tool Kit Development Progress
S/No | Functionalities | Owner | Target Start date | Target Completion Date | Actual Start Date | Actual Completion Date | Status | Remarks
User Interface
1 | Home | MQ | 2015-05-18 | 2015-05-18
2 | Client Profile | MQ | 2015-05-18 | 2015-05-18
3 | Client Detail | MQ | 2015-05-19 | 2015-05-19
4 | Client Listing | MQ | 2015-05-18 | 2015-05-18
5 | Client Attendance | MQ | 2015-05-19 | 2015-05-19
6 | Equipment | MQ | 2015-05-18 | 2015-05-18
7 | Equipment - rental | MQ | 2015-05-18 | 2015-05-18
8 | Equipment Listing | MQ | 2015-05-18 | 2015-05-18
9 | Equipment Rental Listing | MQ | 2015-05-18 | 2015-05-18
10 | Courses | MQ | 2015-05-18 | 2015-05-18
11 | Courses Listing | MQ | 2015-05-18 | 2015-05-18
12 | Courses Registration Listing | MQ | 2015-05-18 | 2015-05-18
13 | Enquiry Create | MQ | 2015-05-18 | 2015-05-18
14 | Enquiry Listing | MQ | 2015-05-18 | 2015-05-18
15 | Appointment - Service Appointment booking(Alignment is not done, the existing page does not have the column called clients) | ZK | 2015-05-18 | 2015-05-18
16 | Invoice Listing(I'm not able to convent ASP.NET button into JavaScript button) | ZK | 2015-05-18 | 2015-05-18
17 | Setup Service Centre(the left slide, the list of Centre is not converted yet) | ZK | 2015-05-18 | 2015-05-18
18 | Setup Subsidy(the left slide, list of Subsidy is not converted) | ZK | 2015-05-18 | 2015-05-18
19 | Setup Means Test Listing(done) | ZK | 2015-05-18 | 2015-05-18
20 | Setup Payment Rate(the left slide is not converted yet) | ZK | 2015-05-18 | 2015-05-18
21 | Setup Programmes | ZK | 2015-05-18 | 2015-05-18
22 | Remove Constiteuncy | ZK | 2015-05-18 | 2015-05-18
23 | Remove Information Source | ZK | 2015-05-18 | 2015-05-18
24 | Remove Corporate Discount | ZK | 2015-05-18 | 2015-05-18
25 | Setup Service Fee | ZK | 2015-05-18 | 2015-05-18
26 | User | ZK | 2015-05-19 | 2015-05-19
27 | Report | ZK | 2015-05-19 | 2015-05-19
28 | Role | ZK | 2015-05-19 | 2015-05-19
Development Features
1 | Filter for client at Home | ZK | 2015-05-20 | 2015-05-20
2 | Values of each Client listed at Home to be real data, currently is fake | ZK | 2015-05-21 | 2015-05-21
3 | Report for Client Arrears with export to excel | MQ | 2015-05-21 | 2015-05-21
4 | Report for Attendance with export to excel | MQ | 2015-05-22 | 2015-05-22
5 | Report for existing client in each centre and programs with export to excel | ZK | 2015-05-22 | 2015-05-22
6 | Report for withdrawal for each centre | ZK | 2015-05-25 | 2015-05-25
7 | Report for Transport services required for each centre | ZK | 2015-05-26 | 2015-05-27